## Tracking Plan - Costs
WBS | Task Name (Activities) | Duration(man-days) | PM | BC | PD | T | U | Roles | Description | Cost | ID | Phase Name | Cost
1 | Voucher Creation Program for Island-Hopping | [6 empty] | PM | Project Manager | 6350 | 1.1 | Initiation Phase | 800
1.1 | Initiation Phase | 4 | 650 | 150 |  |  |  | BC | Booking Coordinator | 900 | 1.2 | Definition Phase | 1900
1.1.1 | Information Gathering | 1 | 300 |  |  |  |  | PD | Program Developer | 3750 | 1.3 | Execution Phase | 5100
1.1.2 | Requirements Analysis | 1 | 150 | 150 |  |  |  | T | Tester | 150 | 1.4 | Control Phase | 2550
1.1.3 | Develop Project Plan | 2 | 200 |  |  |  |  | U | User | 300 | 1.5 | Close Out Phase | 1100
1.2 | Definition Phase | 43 | 1900 | [8 empty] | Project Cost | 11450
1.2.1 | Create Project Model System | 2 | 200
1.2.2 | Create Project Methodology | 2 | 200
1.2.3 | Create Work Breakdown Structure | 2 | 200
1.2.4 | Define Project Team | 2 | 200
1.2.5 | Determine Project Costs | 14 | 400
1.2.6 | Develop Project Development Monitoring | 6 | 400
1.2.7 | Project Approval | 15 | 300
1.3 | Execution Phase | 43 | 1100 | 350 | 3350 | 150 | 150
1.3.1 | Verify & Validate User Requirements | 2 | 150 | 150
1.3.2 | Design Program Layout | 5 |  |  | 500
1.3.3 | Integrate Booking Function | 6 |  |  | 750
1.3.4 | Integrate Guest Information Database | 6 |  |  | 750
1.3.5 | Integrate Save and Print Function | 6 |  |  | 750
1.3.6 | Testing Phase | 4 | 300 |  |  | 150
1.3.7 | System Revision | 4 |  |  | 400
1.3.8 | Install Live System | 2 | 200 |  | 200
1.3.9 | User Training | 6 | 300 | 200 |  |  | 150
1.3.10 | Go Live | 2 | 150
1.4 | Control Phase | 19 | 1750 | 400 | 400
1.4.1 | Project Management | 10 | 750 | 200
1.4.2 | Project Status Reporting | 3 | 400
1.4.3 | Issue Resolution | 3 | 200 |  | 400
1.4.4 | Update Project Management Plan | 3 | 400 | 200
1.5 | Close Out Phase | 9 | 950 |  |  |  | 150
1.5.1 | User Acceptance | 2 | 250 |  |  |  | 150
1.5.2 | Documentation | 5 | 300
1.5.3 | Project Handover | 1 | 200
1.5.4 | Project Closure | 1 | 200
TOTAL |  | 118 | 6350 | 900 | 3750 | 150 | 300

## Tracking Plan - Schedule
Project Milestone | Target Date | Actual Date
Information Gathering | 2024-01-22 | 2024-01-22
Requirements Analysis | 2024-01-23 | 2024-01-22
Develop Project Plan | 2024-01-25 | 2024-01-25
Create Project Model System | 2024-02-02 | 2024-02-02
Create Project Methodology | 2024-02-02 | 2024-02-02
Create Work Breakdown Structure | 2024-02-02 | 2024-02-04
Define Project Team | 2024-02-02 | 2024-02-06
Determine Project Costs | 2024-02-16 | 2024-02-16
Develop Project Development Monitoring | 2024-02-22 | 2024-02-28
Project Approval | 2024-03-08
Verify & Validate User Requirements | 2024-03-10
Design Program Layout | 2024-03-15
Integrate Booking Function | 2024-03-21
Integrate Guest Information Database | 2024-03-27
Integrate Save and Print Function | 2024-04-02
Testing Phase | 2024-04-06
System Revision | 2024-04-10
Install Live System | 2024-04-12
User Training | 2024-04-16
Go Live | 2024-04-18
Project Management | 2024-04-28
Project Status Reporting | 2024-05-01
Issue Resolution | 2024-05-04
Update Project Management Plan | 2024-05-07
User Acceptance | 2024-05-09
Documentation | 2024-05-14
Project Handover | 2024-05-15
Project Closure | 2024-05-16

## Tracking Plan - Quality
Metric | Measures | Target
Bug Ratio | Number of bugs logged / Total number of Test Case Scenario | 10%
Issue Ratio | Number of Open issue / Total number of Logged issues | 5%
Pass Modules Ratio | Number of bugs logged / Total number of Test Case | 100%

## Dashboard
Project Dashboard - Voucher Creation App for Island -Hopping
PROJECT BUDGET: 11,450 Php
Team Leader:
Joshua Arnel A. Gonzales Members: Joshua Arnel A. Gonzales

## Data
Completed | 32% | Phase Name | Target Budget | Actual Budget | Timeboxing | Target Days | Actual Days | Category | Bugs | Issues
In-progress | 68% | Initation Phase | 800 | 200 | Information Gathering | 1 | 1 | Recurring | 3 | 2
|  | Definition Phase | 1900 | 300 | Requirements Analysis | 0.5 | 0.5 | Solved | 10 | 5
|  | Execution Phase | 5100 |  | Develop Project Plan | 1 | 1 | Unresolved | 3 | 1
|  | Control Phase | 2550 |  | Create Project Model System | 2 | 2
|  | Close Out Phase | 1100 |  | Create Project Methodology | 2 | 2
[5 empty] | Create Work Breakdown Structure | 2 | 4
[5 empty] | Define Project Team | 2 | 6
[5 empty] | Determine Project Costs | 7 | 7
[5 empty] | Develop Project Development Monitoring | 7 | 13
[5 empty] | Project Approval | 2
[5 empty] | Verify & Validate User Requirements | 0.5
[5 empty] | Design Program Layout | 4
[5 empty] | Integrate Booking Function | 6
[5 empty] | Integrate Guest Information Database | 6
[5 empty] | Integrate Save and Print Function | 6
[5 empty] | Testing Phase | 2
[5 empty] | System Revision | 4
[5 empty] | Install Live System | 1
[5 empty] | User Training | 2
[5 empty] | Go Live | 1
[5 empty] | Project Management | 6
[5 empty] | Project Status Reporting | 2
[5 empty] | Issue Resolution | 4
[5 empty] | Update Project Management Plan | 2
[5 empty] | User Acceptance | 2
[5 empty] | Documentation | 3
[5 empty] | Project Handover | 1.5
[5 empty] | Project Closure | 1

## Bugs
Category | Bugs | Issues
Recurring | 3 | 2
Solved | 10 | 5
Unresolved | 3 | 1

## Timeboxing
Timeboxing | Target Days | Actual Days
Information Gathering | 1 | 1
Requirements Analysis | 0.5 | 0.5
Develop Project Plan | 1 | 1
Create Project Model System | 2 | 2
Create Project Methodology | 2 | 2
Create Work Breakdown Structure | 2 | 4
Define Project Team | 2 | 6
Determine Project Costs | 7 | 7
Develop Project Development Monitoring | 7 | 13
Project Approval | 2
Verify & Validate User Requirements | 0.5
Design Program Layout | 4
Integrate Booking Function | 6
Integrate Guest Information Database | 6
Integrate Save and Print Function | 6
Testing Phase | 2
System Revision | 4
Install Live System | 1
User Training | 2
Go Live | 1
Project Management | 6
Project Status Reporting | 2
Issue Resolution | 4
Update Project Management Plan | 2
User Acceptance | 2
Documentation | 3
Project Handover | 1.5
Project Closure | 1

## Progress
Completed | 32%
In-progress | 68%

## Target and Actual Budget
Phase Name | Target Budget | Actual Budget
Initation Phase | 800 | 200
Definition Phase | 1900 | 300
Execution Phase | 5100
Control Phase | 2550
Close Out Phase | 1100