## Sheet1
WBS | Task Name (Activities) | Duration(man-days) | PM | BC | PD | Roles | Description | Cost | ID | Phase Name | Cost
1 | Voucher Creation Program for Island-Hopping |  |  |  |  | PM | Project Manager | 6350 | 1.1 | Initiation Phase | 800
1.1 | Initiation Phase | 4 | 650 | 150 |  | BC | Booking Coordinator | 1350 | 1.2 | Definition Phase | 1900
1.1.1 | Information Gathering | 1 | 300 |  |  | PD | Program Developer | 3750 | 1.3 | Execution Phase | 5000
1.1.2 | Requirements Analysis | 1 | 150 | 150 |  |  |  |  | 1.4 | Control Phase | 2600
1.1.3 | Develop Project Plan | 2 | 200 | [5 empty] | 1.5 | Close Out Phase | 1150
1.2 | Definition Phase | 43 | 1900 | [6 empty] | Project Cost | 11450
1.2.1 | Create Project Model System | 2 | 200
1.2.2 | Create Project Methodology | 2 | 200
1.2.3 | Create Work Breakdown Structure | 2 | 200
1.2.4 | Define Project Team | 2 | 200
1.2.5 | Determine Project Costs | 14 | 400
1.2.6 | Develop Project Development Monitoring | 6 | 400
1.2.7 | Project Approval | 15 | 300
1.3 | Execution Phase | 43 | 1100 | 550 | 3350
1.3.1 | Verify & Validate User Requirements | 2 | 150 | 150
1.3.2 | Design Program Layout | 5 |  |  | 500
1.3.3 | Integrate Booking Function | 6 |  |  | 750
1.3.4 | Integrate Guest Information Database | 6 |  |  | 750
1.3.5 | Integrate Save and Print Function | 6 |  |  | 750
1.3.6 | Testing Phase | 4 | 300 | 200
1.3.7 | System Revision | 4 |  |  | 400
1.3.8 | Install Live System | 2 | 200 |  | 200
1.3.9 | User Training | 6 | 300 | 200
1.3.10 | Go Live | 2 | 150
1.4 | Control Phase | 19 | 1750 | 450 | 400
1.4.1 | Project Management | 10 | 750 | 200
1.4.2 | Project Status Reporting | 3 | 400
1.4.3 | Issue Resolution | 3 | 200 |  | 400
1.4.4 | Update Project Management Plan | 3 | 400 | 250
1.5 | Close Out Phase | 9 | 950 | 200
1.5.1 | User Acceptance | 2 | 250 | 200
1.5.2 | Documentation | 5 | 300
1.5.3 | Project Handover | 1 | 200
1.5.4 | Project Closure | 1 | 200
TOTAL |  | 118 | 6350 | 1350 | 3750